## Sheet1
Jacob Brink:
Did begin work in group with Jack Vandermolen and Aaron Ttojelk.
Total Hours: 51.5
Cardboard Canoe Contest
Canoe Construction
Canoe Testing
Oars
(Person 1)
Hull
(Person2)
Rudder
(Jacob)
Strength Test
(All Team)
Stability Test
(Place on pivot board and test balance. Adjust construction if imbalance occurs
(Jacob, Person2)
(2.5 hours)
Waterproof
Test
(Carefully place in water)
(Jacob,Person1)
(3 hours)
Maximum Weight
Test
(Place dumbells in boat until it starts to sink. Record final weight
(Person2)
(2 hours)
Research
(Research other teams' designs and find best shape and materials )
(Person2)
(3 hours)
Purchase Materials
(Purchase only contestable grade material)
(Person2)
(3.5 hours)
Construction
(Bulid hull carefully and possibly with aid)
(Person2)
(7 hours)
Research
(Figure out ideal shape of paddle)
(Person1)
(2 hours)
Purchase Materials
(Travel, find, and buy needed materials)
(Person1)
(4 hours)
Construction
(Assemble materials into oar)
(Person1)
(5 hours)
Research
(Research best rudder to steer boat and yet is lightweight)
(Jacob)
(4 hours)
Purchase Materials
(Find rudder material and buy it)
(Jacob)
(2 hours)
Construction
(Construct rudder for steering)
(Jacob)
(1.5 hours)
Assign Roles
(Choose two rowers and one leader)
(ALL)
(1 hour)
Gym Training
(Lose weight and get strong for rowing)
(Rowers as defined in "Assign Roles" 3.a task)
(10 hours)
Crew Training
Canoe Assembly
(All of Team)
(1 hour)
1
2
3
3.a
3.b
2.b
2.a
2.a.i
2.a.ii
1.a
1.b
1.c
1.d
1.a.i
1.a.i.1
1.a.i.1.a
1.b.i
1.b.i.1
1.b.i.1.a
1.c.i
1.c.i.1
1.c.i.1.a
1
1
2
3.a
1.a.i
1.a.i.1
1.b.i
1.b.i.1
1.c.i
1.c.i.1
1.a,1.b,1.c
Task that must be completed
Task Number
Task Description